## Report
Date | Task Name | Status | Person
2024-11-11 | Create input data | Incomplete | Adriean
2024-11-12 | Started module outline | Incomplete | Nicholas
2024-11-12 | Started flow diagram | Complete | Adriean
2024-11-12 | Created PA report | Complete | Adriean
2024-11-12 | Wrote pseudo for Config.py | Complete | Chris
2024-11-12 | Updated outline | Complete | Nicholas
2024-11-12 | Wrote pseudo for Departments module | Incomplete | Adriean
2024-11-12 | Wrote pseudo for Individuals module | Complete | Chris
2024-11-13 | Wrote pseudo for Departments module | Complete | Adriean
2024-11-13 | Updated input data | Complete | Adriean
2024-11-13 | Wrote pseudo for main.py | Complete | Nicholas
2024-11-14 | Created Config.py | Complete | Adriean
2024-11-14 | Created Individuals.py | Complete | Adriean
2024-11-19 | Set up dictionary for configs in Individuals.py | Complete | Adriean
2024-11-19 | Worked on csv import methods | Complete | Nicholas
2024-11-19 | Worked on dataframe objects in Individuals.py | Complete | Nicholas
2024-11-19 | Worked on line graphs in Individuals.py | Complete | Nicholas
2024-11-20 | Worked on query functionality in Individuals.py | Complete | Chris
2024-11-20 | Worked on violin plots in Individuals.py | Complete | Chris
2024-11-20 | Cleaned up Individuals.py | Complete | Chris
2024-11-20 | Tested method functionality of Individuals.py | Complete | Chris
2024-11-20 | Cleaned up Individuals.py | Complete | Adriean
2024-11-20 | Updated methods for calculating fitness scores | Complete | Adriean
2024-11-20 | Updated method to view person fitness status | Complete | Adriean
2024-11-21 | Updated outline of Departments.py | Complete | Adriean
2024-11-21 | Defined tasks for PA3 milestone in GitHub | Complete | Adriean
2024-11-26 | Created functionality for vector plotting | Complete | Adriean
2024-11-26 | Created and updated Departments.py | Complete | Adriean
2024-11-26 | Updated Individuals.py and GitHub outlines | Complete | Adriean
2024-11-26 | Updated project diagram | Complete | Adriean
2024-11-26 | Created and updated Interface.py and Main.py | Complete | Adriean
2024-11-27 | Worked on getSteps() for Departments.py | Complete | Chris
2024-11-27 | Worked on getHrv() for Departments.py | Complete | Chris
2024-11-27 | Worked on getFitnessScores() for Departments.py | Incomplete | Chris
2024-11-28 | Worked on getFitnessScores() for Departments.py | Complete | Chris
2024-11-28 | Worked on calcDays() for Departments.py | Complete | Chris
2024-11-29 | Worked on generating department dataframes and statistics | Incomplete | Chris
2024-11-29 | Updated Individuals.py | Complete | Adriean
2024-11-29 | Set up interface for individuals | Complete | Adriean
2024-11-29 | Set up interface for departments | Incomplete | Adriean
2024-11-29 | Added config for probation fitness score | Complete | Adriean
2024-11-29 | Worked on calcAvgAge() | Complete | Nicholas
2024-11-29 | Worked on calcAvgFitnessScore() | Complete | Nicholas
2024-11-29 | Worked on generating department dataframes and statistics | Complete | Chris
2024-11-30 | Worked on writing statistics out | Complete | Chris
2024-11-30 | Created all department histograms | Complete | Nicholas
2024-11-30 | Worked on pickleSave() and pickleLoad() | Complete | Chris
2024-12-03 | Defined work to be completed for next milestone in GitHub | Complete | Adriean
2024-12-03 | Made miscellaneous fixes to code | Complete | Adriean
2024-12-03 | Added logging to methods of Departments.py | Complete | Adriean
2024-12-03 | Added probability methods to Departments.py | Complete | Adriean
2024-12-03 | Added unique value combinations/permutations to Departments.py | Complete | Adriean
2024-12-03 | Added orthogonality vector to vector plot | Complete | Adriean
2024-12-03 | Fixed bugs with loading pickle file | Complete | Adriean
2024-12-05 | Cleaned up modules | Complete | Adriean
2024-12-05 | Updated diagrams | Complete | Adriean
2024-12-05 | Write project report (except user manual) | Complete | Adriean