## Report
Date | Task Name | Status | Person
2024-11-11 | Create input data | Incomplete | Adriean
2024-11-12 | Started module outline | Incomplete | Nicholas
2024-11-12 | Started flow diagram | Complete | Adriean
2024-11-12 | Created PA report | Complete | Adriean
2024-11-12 | Wrote pseudo for Config.py | Complete | Chris
2024-11-12 | Updated outline | Complete | Nicholas
2024-11-12 | Wrote pseudo for Departments module | Incomplete | Adriean
2024-11-12 | Wrote pseudo for Individuals module | Complete | Chris
2024-11-13 | Wrote pseudo for Departments module | Complete | Adriean
2024-11-13 | Updated input data | Complete | Adriean
2024-11-13 | Wrote pseudo for main.py | Complete | Nicholas
2024-11-14 | Created Config.py | Complete | Adriean
2024-11-14 | Created Individuals.py | Complete | Adriean
2024-11-19 | Set up dictionary for configs in Individuals.py | Complete | Adriean
2024-11-19 | Worked on csv import methods | Complete | Nicholas
2024-11-19 | Worked on dataframe objects in Individuals.py | Complete | Nicholas
2024-11-19 | Worked on line graphs in Individuals.py | Complete | Nicholas
2024-11-20 | Worked on query functionality in Individuals.py | Complete | Chris
2024-11-20 | Worked on violin plots in Individuals.py | Complete | Chris
2024-11-20 | Cleaned up Individuals.py | Complete | Chris
2024-11-20 | Tested method functionality of Individuals.py | Complete | Chris