## Report
Date | Task Name | Status | Person
2024-11-11 | Create input data | Incomplete | Adriean
2024-11-12 | Started module outline | Incomplete | Nicholas
2024-11-12 | Started flow diagram | Complete | Adriean
2024-11-12 | Created PA report | Complete | Adriean
2024-11-12 | Wrote pseudo for Config.py | Complete | Chris
2024-11-12 | Updated outline | Complete | Nicholas
2024-11-12 | Wrote pseudo for Departments module | Incomplete | Adriean
2024-11-12 | Wrote pseudo for Individuals module | Complete | Chris
2024-11-13 | Wrote pseudo for Departments module | Complete | Adriean
2024-11-13 | Updated input data | Complete | Adriean
2024-11-13 | Wrote pseudo for main.py | Complete | Nicholas